## Status Report
Status Report for Team 4
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-10 | Overall Status: | Yellow
Contact: | Alex | Explanation: | Wireframes complete, starting to brainstorm for schema
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Wireframe design, schema work
Alex | Wireframe design, schema work
Ken | Wireframe design, schema work
Ted | Wireframe design, schema work
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | NA
Back-end |  | NA
Business logic |  | NA
Front-end |  | NA
Testing |  | NA
Presentation (Wireframes) |  | Good | 2020-09-10 | 100%
Database |  | NA