## Status Report
Status Report for Team 4
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-11 | Overall Status: | Yellow
Contact: | Alex | Explanation: | Laid out ERD and made a dummy schema. Expecting it to change over time. Got a React + Spring app set up but no actual code yet. Figured out merging on Git.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Cracked the gitignore bug
Alex | Dummy schema
Ken | Teaching everyone else how to merge on Github
Ted | Created ERD and provided absolute banter throughout day
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | NA
Back-end |  | Started |  | 5, 10% tops
Business logic |  | NA
Front-end |  | NA
Testing |  | NA
Presentation |  | Good | 2020-09-10 | 100%
ERD |  | Good |  | 80%