## Status Report
Status Report for Team 4
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-14 | Overall Status: | Green
Contact: | Alex | Explanation: | Entities have been completed. Jdbc query functions are almost done. Tests for completed entities are done.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Trade entity, TradeDao, ERD updates
Alex | UserDao, User Testing, wrote data dictionary
Ken | Order entitiy, OrderDao
Ted | OpeningPrice + Share entities and Daos
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | Started |  | 66%
Back-end |  | Started |  | 52%
Business logic |  | NA |  | 0%
Front-end |  | NA |  | 0%
Testing |  | Started |  | 20%
Presentation |  | NA |  | 0%
ERD |  | Good |  | 90%