## Status Report
Status Report for Team 4
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-15 | Overall Status: | Green
Contact: | Alex | Explanation: | After finishing entities, we wrote our tests and merged everything together. There are a couple more tests to write before the service layer is started.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Trade Testing
Alex | User Testing
Ken | Order Testing
Ted | Share and Price Testing
ID # | Key Issues | Action Plan |  |  | Status
None
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | Started |  | 66%
Back-end |  | Good |  | 80%
Business logic |  | NA |  | 0%
Front-end |  | NA |  | 0%
Testing |  | Good |  | 80%
Presentation |  | NA |  | 0%
ERD |  | Good |  | 95%