## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-16 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | Today we finished our service layer. One half worked on service layer testing while the other began developing the controllers for the front end.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Trade Service, Auto-generated service, ServiceLayer tests
Alex | User Service, Controller
Ken | Order Service, misc. service, ServiceLayer tests
Ted | Share and Price Service, Controller
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 90%
Back-end |  |  | Good |  | 90%
Business logic |  |  | Started |  | 50%
Front-end |  |  | NA |  | 0%
Testing |  |  | Good |  | 80%
Presentation |  |  | NA |  | 0%
ERD |  |  | Good |  | 95%