## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-17 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | We made the stubs for our service layer tests and finished those. We now have a fully tested back-end for our front-end.
Prepared By:
A React + REST front-end was created and can display data from our database. Next is to design the pages after our wireframes.
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Created stubs and wrote service layer tests
Alex | Created front-end in React
Ken | Controller edits
Ted | Share and Price Controller
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 95%
Business logic |  |  | Good |  | 90%
Front-end |  |  | Started |  | 2%
Testing |  |  | Good |  | 95%
Presentation |  |  | NA |  | 0%
ERD |  |  | Good |  | 95%
Architecture Document |  |  | Started |  | 10%