## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-18 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | We figured out how to create tables for our trades and orders and get them displayed with React. We then split up to work on individual components.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Ticker Feed, Create Order components
Alex | TradeList component
Ken | User component
Ted | Buy/Sell order component
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 95%
Business logic |  |  | Good |  | 90%
Front-end |  |  | Started |  | 20%
Testing |  |  | Good |  | 95%
Presentation |  |  | NA |  | 0%
ERD |  |  | Good |  | 100%
Architecture Document |  |  | Started |  | 10%