## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-21 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | Our line chart can now display an x-axis of date/time and y-axis of price, mimicking a stock graph. Trades can now be searched by dates, prices or amounts.
Prepared By:
Front end components are 2/3 finished, next is gathering them to display on each page.
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Worked on the OrderForm (create order) component
Alex | Finished Last 10 Trades table
Ken | Researched ways to refresh data live, finished search function
Ted | Got the graph functioning
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 96%
Business logic |  |  | Good |  | 95%
Front-end |  |  | Started |  | 33%
Testing |  |  | Good |  | 95%
Presentation |  |  | NA |  | 0%
ERD |  |  | Good |  | 100%
Architecture Document |  |  | Started |  | 10%