## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-22 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | The front-end React components and most of the documentation are completed. We can navigate between the pages of the site. Still working on getting everything updating live as orders come through.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Finished updating Create Order component
Alex | Completed Architecture Document, completed Edit Orders page
Ken | Implemented Socket.IO
Ted | Completed Architecture Document
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 96%
Business logic |  |  | Good |  | 95%
Front-end |  |  | Started |  | 70%
Testing |  |  | Good |  | 95%
Presentation |  |  | NA |  | 0%
ERD |  |  | Good |  | 100%
Architecture Document |  |  | Good |  | 100%