## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-23 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | We are near completion. The front end is nearly done and needs some paint. A few small documentation items left to finish off, too.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Created KTC information display
Alex | Created powerpoint presentation
Ken | Finished search trades page
Ted | Put together navbar
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 100%
Business logic |  |  | Good |  | 100%
Front-end |  |  | Good |  | 75%
Testing |  |  | Good |  | 95%
Presentation |  |  | Started |  | 50%
ERD |  |  | Good |  | 100%
Architecture Document |  |  | Good |  | 100%