## Status Report
Status Report for Team 4
Project |  |  | Status: (Red/Yellow/Green)
Date: | 2020-09-24 |  | Overall Status: | Green
Contact: | Alex |  | Explanation: | Finished project and prepared for presentation.
Prepared By:
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Aman | Final component
Alex | Finalized documentation and order/trades pages
Ken | Linking all pages
Ted | Styling for pages
ID # | Key Issues |  | Action Plan |  |  | Status
None
Milestone Key
Late stages | Early stages | Not started | SOS
Critical Milestones |  |  | Health | Due Date | Comment/Status
Environment setup |  |  | Good |  | 100%
Back-end |  |  | Good |  | 100%
Business logic |  |  | Good |  | 100%
Front-end |  |  | Good |  | 100%
Testing |  |  | Good |  | 100%
Presentation |  |  | Good |  | 100%
ERD |  |  | Good |  | 100%
Architecture Document |  |  | Good |  | 100%